## Estimate
ESTIMATE
Repairing, overhauling of PH-2 EOT crane control panel including laying of power and control cables.
SL | DESCRIPTION | QTY | UNIT | RATE | AMOUNT
1 | Control transformer 1kVA, 440V/220V/110V. | 2 | nos | 6800 | 13600
2 | MCCB 100A triple pole | 2 | nos | 5700 | 11400
3 | Earth leakage relay with CBCT, 110V coil | 2 | nos | 9500 | 19000
4 | PVC single core flexible cable 10sqmm | 150 | m | 70 | 10500
5 | Auxiliary contactor 4NO+4NC, 110V coil | 20 | nos | 1200 | 24000
6 | Push button switch with inner contacts | 10 | nos | 860 | 8600
7 | Power contactor 3-pole, 110V coil, 70A | 4 | nos | 2300 | 9200
8 | Lockabel emergency switch | 1 | no | 450 | 450
9 | LED pilot lamp, red/yellow/blue/green | 10 | nos | 350 | 3500
10 | Thermal overload relay, 60-90A, | 2 | nos | 2500 | 5000
11 | PVC Felxible single core cable, 2.5sqmm | 300 | m | 22 | 6600
12 | Cable terminal block, 16sqmm | 100 | nos | 25 | 2500
13 | Cable terminal block, 35sqmm | 40 | nos | 40 | 1600
14 | Limit switch, 2NO+2NC | 4 | nos | 6450 | 25800
15 | Labour cost for overhauling of panels, removal of damaged cables and laying of new cables including contractor profit. | 1 | job | 51321.6 | 51321.6 | 377.4%
TOTAL |  |  |  |  | 193072
GST @ 18% |  |  |  |  | 34753
TOTAL WITH GST |  |  |  |  | 227825
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP

## Labour Analysis
LABOUR COST ANALYSIS
Repairing, overhauling of PH-2 EOT crane control panel including laying of power and control cables.
Works: | Following works are required for repairing/overhauling of the EOT crane.
| 1 | Dismantling of old damaged panel.
| 2 | Removal of old damaged power and control cable.
| 3 | Fixing of supply items into the panel.
| 4 | Wiring of control panel.
| 5 | Laying and fixing of power and control cables.
| 6 | Bunching and festooning of flexible cables.
| 7 | Testing and commissioning.
Cost : | The defined work for each motor can be carried out by a gang of
4 skilled and 4 unskilled labourers in 12 shifts.
|  | TYPE | MANSHIFTS | RATE | AMOUNT | SKILLED | 4
|  | SKILLED | 48 | 569 | 27312 | UNSKILLED | 4
|  | UN SKILLED | 48 | 403 | 19344 | SHIFTS | 12
|  | LABOUR COST |  |  | 46656
|  | CONTRACTOR PROFIT @ 10% |  |  | 4665.6
|  | TOTAL |  |  | 51321.6
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP

## Material Analysis
MATERIAL ANALYSIS
Repairing, overhauling of PH-2 EOT crane control panel including laying of power and control cables.
SL | ITEM | QTY BASIS | QTY | UNIT | RATE BASIS | RATE
1 | Control transformer 1kVA, 440V/220V/110V. | Actual | 2 | nos | Rate as per wo no : DCH/GM(E&M)/WO/CHP/19-20/76 dtd. 15.11.19 | 6800
2 | MCCB 100A triple pole | Actual | 2 | nos | As above | 5700
3 | Earth leakage relay with CBCT, 110V coil | Actual | 2 | nos | As above | 9500
4 | PVC single core flexible cable 10sqmm | Actual | 150 | m | As above | 70
5 | Auxiliary contactor 4NO+4NC, 110V coil | Actual | 20 | nos | As above | 1200
6 | Push button switch with inner contacts | Actual | 10 | nos | As above | 860
7 | Power contactor 3-pole, 110V coil, 70A | Actual | 4 | nos | As above | 2300
8 | Lockabel emergency switch | Actual | 1 | no | As above | 450
9 | LED pilot lamp, red/yellow/blue/green | Actual | 10 | nos | As above | 350
10 | Thermal overload relay, 60-90A, | Actual | 2 | nos | As above | 2500
11 | PVC Felxible single core cable, 2.5sqmm | Actual | 300 | m | As above | 22
12 | Cable terminal block, 16sqmm | Actual | 100 | nos | As above | 25
13 | Cable terminal block, 35sqmm | Actual | 40 | nos | As above | 40
14 | Limit switch, 2NO+2NC | Actual | 4 | nos | As per global LPP dated 08-12-2020 | 6450
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP