## Estimate
ESTIMATE
Filtration of transformer oil in different transformers at CHP, Dudhichua.
SL | DESCRIPTION | QTY | UNIT | RATE (Rs) | AMOUNT (Rs)
1 | Draining of transformer oil, filteration and refilling of the same into the respective transformers. | 10335 | ltrs | 16.17 | 167116.95
GST @ 18% |  |  |  |  | 30081.051
TOTAL WITH GST |  |  |  |  | 197198.001
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP

## Labour Analysis-null
LABOUR COST ANALYSIS
Filtration of transformer oil in different transformers at CHP, Dudhichua.
Works: | 1 | Dismantling work.
| 2 | Taking out of burnt coils.
| 3 | Making coil of new copper wire.
| 4 | Fixing of new coils in place.
| 5 | Fitting of terminal bushes.
| 6 | Reassembly work.
| 7 | Heating.
| 8 | Testing.
Manpower: |  | TYPE | QTY | RATE | AMOUNT
HIGHLY SKILLED
|  | SKILLED | 2 | 506 | 1012
SEMI SKILLED
|  | UN SKILLED | 2 | 359 | 718
|  | PER DAY LABOUR COST |  |  | 1730
|  | NO OF DAYS REQUIRED |  |  | 40
|  | TOTAL LABOUR COST |  |  | 69200
|  | CONTRACTOR PROFIT @ 10% |  |  | 6920
|  | GRAND TOTAL |  |  | 76120
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP

## Material Analysis
QUANTITY AND RATE ANALYSIS
Filtration of transformer oil in different transformers at CHP, Dudhichua.
SL | ITEM | QUANTITY ESTIMATION |  |  | RATE JUSTIFICATION
|  | Basis | Qty | Unit | Basis | Rete per Unit (in Rs.) | Rete per Unit excluding Taxes (in Rs.)
2 | Draining of transformer oil, filteration and refilling of the same into the respective transformers. | Transformerwise quantity of oil has been enclosed. | 10335 | ltrs | Rate as per wo no : DCH/DGM(E&M)/WO/33KV/14-15/64 DTD 09.09.2014 | 17 | 17
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP

## transformers
Details of transformers at CHP
SL | Location | Rating in kVA | VoLtage ratio | Oil Quantity in litres | serial
1 | SS-1 | 1000 | 6600/433 | 1000 | T84295
2 | SS-1 | 1000 | 6600/433 | 1000 | T84296
3 | SS-2 | 1500 | 6600/433 | 1500 | T84309
4 | SS-2 | 1500 | 6600/433 | 1500 | T84310
5 | SS-4 | 1000 | 6600/433 | 650 | ND4431
6 | SS-4 | 1000 | 6600/433 | 650 | ND4433
7 | SS-5 | 1000 | 6600/433 | 650 | ND4424
8 | SS-5 | 1000 | 6600/433 | 650 | ND4425
9 | SS-6 | 630 | 6600/433 | 615 | JC02701
10 | SS-6 | 630 | 6600/433 | 615 | JC02702
11 | SS-1 | 100 | 6600/220 | 160 | T03188
12 | SS-1 | 100 | 6600/220 | 175 | T10306
13 | SS-2 | 100 | 6600/220 | 160 | 320
14 | SS-3 | 75 | 6600/433 | 225 | 1262
15 | SS-3 | 100 | 6600/220 | 210 | 12791
16 | SS-4 | 50 | 6600/220 | 115 | KF338
17 | SS-4 | 100 | 6600/220 | 160 | 3112
18 | SS-5 | 100 | 6600/220 | 160 | 3117
19 | SS-6 | 100 | 6600/220 | 140 | 826
Total quantity of oil |  |  |  | 10335
I/c CHP-DCH |  |  | Dy Mgr(E&M)/CHP |  | SOE(E&M)/CHP