## Estimate
ESTIMATE
Overhauling of cable trollies and cable replacement for 3 nos travelling tippers of CHP, Dudhichua Project.
SL | DESCRIPTION | QTY | UNIT | RATE | AMOUNT
1 | Overhauling of cable trollies of three nos trippers of CHP of Dudhichua Project by: Dismantling 500m of old power and control cables. Dismantling of 102 nos trollies from structure and refitting after checking, fixing and greasing. Laying of new 500m power and control cables (departmentally provided) on trollies and fixing the cables with ties. The cable trollies are at a height of about 20 feet from base structure. The work will need a gang of at least 2 skilled and 3 unskilled manpower. The site will be available as per plant shutdown schedule. | 1 | job | 70408.8 | 70408.8
TOTAL |  |  |  |  | 70409
GST @ 18% |  |  |  |  | 12674
TOTAL WITH GST |  |  |  |  | 83083
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP

## Sheet1
LABOUR COST ANALYSIS
Overhauling of cable trollies and cable replacement for 3 nos travelling tippers of CHP, Dudhichua Project.
Following works are involved.
| 1 | Dismantling of 500m old power and control cables |  |  |  | 3
| 2 | Dismantling of trollies. |  |  |  | 4
| 3 | Cleaning, checking and greasing of trollies. |  |  |  | 3
| 4 | Refitting of conditioned trollies |  |  |  | 3
| 5 | Laying of cables on trollies |  |  |  | 3
| 6 | Tying the cables with trollies with cable ties. |  |  |  | 2
The defined work for three tippers can be carried out by a gang of
2 skilled and 6 unskilled labors in 18 shifts.
|  | TYPE | MANSHIFTS | RATE | AMOUNT | Skilled | 2
|  | SKILLED | 36 | 569 | 20484 | Unskilled | 6
|  | UN SKILLED | 108 | 403 | 43524 | Shifts | 18
|  | TOTAL |  |  | 64008
|  | CONTRACTOR PROFIT @ 10% |  |  | 6400.8
|  | LABOR COST PER MOTOR |  |  | 70408.8
Incharge/CHP Dy.Mgr(E&M)/CHP SOE(E&M)/CHP Foreman/CHP